## Sheet1
GROUP 8 - Project Timeline
Date Assigned | Agenda | Submitted On | Deadline
2026-04-17 | Assigning of the Roles of each Member | - | -
2026-04-25 | Conceptualizing Project Ideas | 2026-04-27 | 2026-04-27
2026-05-04 | Finalized Idea and Logic of the Program | 2026-05-05 | 2026-05-06
2026-05-07 | Creation of the UML Diagram | 2026-05-07 | 2026-05-10
| UI/UX Prototype of the Website Starts | 2026-05-12 | 2026-05-14
| Skeletal Code was started. | - | -
2026-05-11 | Code Submission to be Tested | 2026-05-13 | 2026-05-13
2026-05-14 | Creating and Editing of PPT | 2026-05-14 | 2026-05-15
2026-05-14 | Finalized Skeletal Code and PPT contents for Initial Presentation in OOP | 2026-05-15 | 2026-05-15
2026-05-15 | Initial Presentation Day | - | -
2026-05-18 | Applying Feedback and Build Features (eg,. Dashboard, Stats, etc) |  | 2026-05-25
Start to Integrate the Backend to the Frontend
2026-05-20 | Checking for the Updates on the Project
2026-05-22 | System Debugging and Error Handling for Integrated Features
2026-05-26 | Final UI Polishing and Preparation of Technical Documentation |  | 2026-05-29
2026-05-31 | In-Person Meeting for the Final Integration of Backend and Frontend |  | -
| Deployment of the Website and Testing |  | 2026-06-03
| Deployment of the Final Website |  | 2026-06-04
2026-06-06 | Final Presentation of the Project |  | -